## Condition Survey 2021 (1)
Code | Priority | Building | P | G | Y | Element | Work Description | Cost | Comments | Cost | Work Completed
C024690 | 1 - Urgent Work | CARETAKER'S BUNGALOW | 1 | D | 21/22 | Atkins - Internal Walls, Windows & Doors - Linings & Finish | Investigate and rectify damp | 17187.81 | BF investigated, roof is fine. Problems with wall insulation which BF have replaced |  | 2022-04-01
C024856 | 1 - Urgent Work | LOWER BUILDING | 1 | D | 21/22 | Atkins - Windows & Doors - Glazing | Reglaze with double glazed units | 247.16 | Staff room - quote asked for in budget for 2022/23
C024857 | 1 - Urgent Work | LOWER BUILDING | 1 | D | 21/22 | Atkins - Floors & Stairs - Screed & Finish | Replace vinyl sheet flooring | 52.72 | completed |  | 2022-04-01
C024859 | 1 - Urgent Work | LOWER BUILDING | 1 | D | 21/22 | Atkins - Ceilings - Finish | Replace individual tiles with medium quality in concealed grid | 494.4 | Now been superceeded by replacement ceiling as falling down. Added to capital program for 2022/23
C024864 | 1 - Urgent Work | LOWER BUILDING | 1 | D | 21/22 | Atkins - Miscellaneous - Health & Safety | Rectify trip hazard | 223.66 | Completed |  | 2022-02-01
C024795 | 1 - Urgent Work | NURSERY MODULAR | 1 | D | 21/22 | Atkins - Windows & Doors - Frames | Allow to replace windows and glazing | 3000 | NO - Windows do not need replacing they have a film on the windows
C024703 | 1 - Urgent Work | UPPER BUILDING | 1 | D | 21/22 | Atkins - Miscellaneous - Health & Safety | Rectify trip hazard | 223.66 | Completed |  | 2022-02-01
C024753 | 1 - Urgent Work | UPPER BUILDING | 1 | D | 21/22 | Atkins - Floors & Stairs - Treads & Risers | Renew stair tread | 79.08 | Completed |  | 2022-01-01
C024769 | 1 - Urgent Work | UPPER BUILDING | 1 | D | 21/22 | Atkins - Miscellaneous - Health & Safety | Rectify trip hazard | 223.66 | By furthersy Year 6 classroom, mising carpet replaced | 0 | 2021-12-01
C025115 | 1 - Urgent Work | CARETAKER'S BUNGALOW | 1 | C | 21/22 | Atkins - Mechanical Services - Ventilation | Replace extract fan | 375.65 | Two extractor fans quote £300-£450. Still waiting for completion, part of 2022/23 plan
C025090 | 1 - Urgent Work | UPPER BUILDING | 1 | C | 21/22 | Atkins - Mechanical Services - Heating | Replacement Required, past its economical life | 36390 | Oil Boiler - No, working fine. look into with BF to do. Waiting for info from BF.
C024863 | 2 - Essential Work | LOWER BUILDING | 2 | D | 21/22 | Atkins - Windows & Doors - Glazing | Reglaze with double glazed units | 494.32 | Is double glazed don’t need to do
C024691 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | C | 2 | Atkins - Fixed Furniture & Fittings - Non Teaching | Renew kitchen base / wall units 1200mm long, including worktop, appliances, ironmongery etc | 2087.5 | Part of 2022/23 budget. Planned once extractor fans installed and checked no condensation issues remain
C024693 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | C | 2 | Atkins - Windows & Doors - Internal & External Doors | Replace softwood door frame | 268.38 | completed |  | 2022-02-01
C024699 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | C | 2 | Atkins - External Walls - Structure | Cut out & repair brickwork to external walls | 230.66 | Wait till after BF completed cavity wall insulation
C024806 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Roof - Drainage | Clean out, overhaul and repair existing gutters and downpipes | 89.46 | part of yearly plan April 2022
C024809 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Floors & Stairs - Screed & Finish | Replace carpet / carpet tiles | 540.64 | propose 23/24
C024812 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 4 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 6563.64 | in good condition on rolling plan
C025053 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Data / Telephone | The installation should be intrusively checked. Where necessary the existing wiring shall be modified with new containment being installed to provide adequate physical separation between LV, ELV and fire alarm systems in accordance with BS EN 50174 and a minimum environmental protection of IP4X. | 3611 | Don’t Agree. Electrics tested as part of 5 year electrical testing. Chursches check fire alarm system, no issues
C025054 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Electrical Installation | Rewire installation generally, including allowance for asbestos R&D survey to to upgrade small power & lighting wiring installation and provide additional small power outlets. | 7222 | don’t agree, inspected under 5 year electrical and 6months visual
C025055 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Emergency Lighting | Replace lighting with LED luminaires on failure | 4079 | ongoing as and when
C025056 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 13700 | ongoing as and when
C025057 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Lighting Controls | Costs included within ref. C025056 | 0
C025059 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Fire Alarms | Consider connection of Fire Alarm system to remote monitoring via the Intruder Alarm | 500 | It is connected
C025060 | 2 - Essential Work | CLASSROOM MODULAR | 2 | C | 2 | Atkins - Electrical Services - Intruder Alarm | Consider connection of Intruder Alarm system to remote monitoring in conjunction with Fire Alarm | 500 | It is connected
C024830 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - External Walls - Linings & Finish | Allow to repair cill | 500 | completed
C024831 | 2 - Essential Work | LOWER BUILDING | 2 | C | 3 | Atkins - External Walls, Windows & Doors - Frames | Renew hardwood door frame | 1000 | Watch, not needed for 5+ yrs
C024833 | 2 - Essential Work | LOWER BUILDING | 2 | C | 3 | Atkins - Redecorations - External | Redecorate external fascias & soffits - (Gloss) | 8539.05 | 2023/24
C024834 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Repair defective or cracked work with bricks 1 brick thick | 1960.6 | Summer 2022
C024838 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Repoint joints in brickwork walls | 1316.5 | Summer 2022
C024840 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Repair defective or cracked work with bricks 1 brick thick | 7842.4 | Ok currently look at again 2023/24 - investigate rendering options
C024842 | 2 - Essential Work | LOWER BUILDING | 2 | C | 3 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 292.4 | 2023/24
C024852 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Ceilings - Finish | Investigate water ingress and rectify. | 4000 | Resource room - no leak. Needs repainting when resource room repainted
C024853 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - External Walls, Windows & Doors - Frames | Replace timber window boards including decoration. | 60 | part of redecoration programme yr 1 2022
C024854 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Internal Walls, Windows & Doors - Linings & Finish | Replace plaster in small areas, including decoration | 115.34 | part of redecortaion Rabbits 2022
C024855 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Sanitary Services - Fittings | Replace timber panels to WHB. | 400 | not needed
C024858 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Floors & Stairs - Screed & Finish | Replace vinyl sheet flooring | 158.16 | Childrens Kitchen? Not needed yet
C024861 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Ceilings - Finish | Replace individual tiles with medium quality in concealed grid | 164.8 | 2022-02-01
C025023 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Data / Telephone | The installation should be intrusively checked. Where necessary the existing wiring shall be modified with new containment being installed to provide adequate physical separation between LV, ELV and fire alarm systems in accordance with BS EN 50174 and a minimum environmental protection of IP4X. | 7222 | Part of 5 year electrical testing and 6 month visual
C025024 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Electrical Installation | Rewire installation generally, including allowance for asbestos R&D survey to to upgrade small power & lighting wiring installation and provide additional small power outlets. | 36110 | Don’t agree
C025025 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Lighting | Replace lighting with LED luminaires on failure | 24474 | ongoing as and when
C025026 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 68500 | ongoing as and when
C025027 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Lighting Controls | Cost included within ref. C025026 | 0
C025029 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Fire Alarms | Consider connection of Fire Alarm systems to remote monitoring via the Intruder Alarm | 0 | It is connected
C025030 | 2 - Essential Work | LOWER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Intruder Alarm | Consider connection of Intruder Alarm system to remote monitoring in conjunction with Fire Alarm | 0 | It is connected
C024803 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Sanitary Services - Fittings | Replace Wash basins and tiling. | 1500 | Look at. Should be less. Included in 2022/23 budget
C025063 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Electrical Installation | Rewire installation generally, including allowance for asbestos R&D survey to to upgrade small power & lighting wiring installation and provide additional small power outlets. | 7222 | Do not agree
C025064 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Emergency Lighting | Replace lighting with LED luminaires on failure | 4079 | ongoing as and when
C025065 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 13700 | ongoing as and when
C025066 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Lighting Controls | Costs included within ref. C025065 | 0
C025068 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Fire Alarms | Consider connection of Fire Alarm system to remote monitoring via the Intruder Alarm | 500 | It is connected
C025069 | 2 - Essential Work | NURSERY MODULAR | 2 | C | 2 | Atkins - Electrical Services - Intruder Alarm | Consider connection of Intruder Alarm system to remote monitoring in conjunction with Fire Alarm. | 500 | It is connected
C024700 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Repoint joints in brickwork walls | 131.65 | 2022
C024701 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Windows & Doors - Internal & External Doors | Replace external aluminum door with glazed unit. | 8000 | 4 wooden doors external. Look at, can be redecorated 2022 but not full replacement added to 2022/23 budget
C024702 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Windows & Doors - Frames | Renew UPVC double glazed casement windows | 1061.08 | staff room ks2 2023
C024705 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - External Areas - Soft Landscaping | Clear soft landscaping generally (defective rubber crumb play area) | 4324.25 |  |  | Completed 2021/22
C024707 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 152 | summer 2022 round by year 4
C024711 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Apply sealant to expansion joint to concrete | 296.52 | 021/22
C024713 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - External Walls - Structure | Cut out & repair brickwork to external walls | 230.66 | 2022 brickwork project
C024714 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Floors & Stairs - Screed & Finish | Redecorate stair treads | 75 |  |  | completed 2021/22
C024716 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - External Walls, Windows & Doors - Frames | Allow to renew sealant around external doors. | 1260 | summer 2022 smallcost
C024719 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Windows & Doors - Internal & External Doors | Remove door set and make good brickwork. | 1500 | summer 2022 with brickwork by library
C024724 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Windows & Doors - Frames | Renew UPVC double glazed casement windows | 2122.16 | Kitchen and kitchen toilet 2023
C024752 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Sanitary Services - Fittings | Refurbish toilets | 8593.9 | Kitchen toilet - look at in 2024
C024755 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Redecorations - Internal | Redecorate wall & ceiling finishes, lining paper & emulsion | 197.68 | ladies toilet redec programme 2024
C024756 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Internal Walls, Windows & Doors - Linings & Finish | Replace plaster in small areas, including decoration | 576.7 | ?part of rolling redec
C024759 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Ceilings - Finish | Replace plasterboard and skim, including decoration | 1647.2 | not required fibre board
C024760 | 2 - Essential Work | UPPER BUILDING | 2 | C | 3 | Atkins - Floors & Stairs - Screed & Finish | Replace carpet tiles | 2952.32 | Buzzards flooring due Feb 2022
C024761 | 2 - Essential Work | UPPER BUILDING | 2 | C | 3 | Atkins - Ceilings - Finish | Renew suspended ceiling | 2952.32 | not required will need to be looke at by BF
C024763 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Redecorations - Internal | Redecorate wall finishes | 667.17 | part of rolling redec - learning hub
C024766 | 2 - Essential Work | UPPER BUILDING | 2 | C | 3 | Atkins - Ceilings - Finish | Renew suspended ceiling | 2477.84 | No BF to look at if required
C024767 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Floors & Stairs - Screed & Finish | Replace carpet / carpet tiles | 1858.45 | Feb 2022
C024771 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Floors & Stairs - Screed & Finish | Allow to replace entrance mat | 600 | ?
C025037 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Data / Telephone | The installation should be intrusively checked. Where necessary the existing wiring shall be modified with new containment being installed to provide adequate physical separation between LV, ELV and fire alarm systems in accordance with BS EN 50174 and a minimum environmental protection of IP4X. | 7222 | part of 5 year electrical, 6 month visual. Inside cupboard. No work required in music room. IT cupboard
C025038 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Electrical Installation | Rewire installation generally, including allowance for asbestos R&D survey to upgrade small power & lighting wiring installation and provide additional small power outlets | 36110 | part of 5 year electrical testing. 6 month visual. No work required in music room
C025039 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Emergency Lighting | Replace lighting with LED luminaires on failure | 24474 | ongoing as and when
C025040 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 68500 | ongoing as and when
C025041 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Lighting Controls | Costs included within ref. C025040 | 0
C025043 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Fire Alarms | Consider connection of Fire Alarm system to remote monitoring via the Intruder Alarm | 500 | It is connected
C025044 | 2 - Essential Work | UPPER BUILDING | 2 | C | 2 | Atkins - Electrical Services - Intruder Alarm | Consider connection of Intruder Alarm system to remote monitoring in conjunction with Fire Alarm | 500 | It is connected
C024694 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | B | 2 | Atkins - Roof - Coverings & Insulation | Allowance for general roofing repairs & maintenance | 4640.85
C024697 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | B | 5 | Atkins - Roof - Drainage | Clean out existing guttering | 444.9
C025110 | 2 - Essential Work | CARETAKER'S BUNGALOW | 2 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C024796 | 2 - Essential Work | NURSERY MODULAR | 2 | B | 2 | Atkins - Roof - Coverings & Insulation | NONE but the flat roof should be inspected and cleared of debris annually | 0
C024709 | 2 - Essential Work | UPPER BUILDING | 2 | B | 2 | Atkins - Roof - Drainage | Clean out existing guttering | 3410.9
C024798 | 3 - Desirable Work | NURSERY MODULAR | 3 | C | 4 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 219.3
C024723 | 3 - Desirable Work | UPPER BUILDING | 3 | C | 4 | Atkins - External Walls - Structure | Rebuild dwarf wall | 250
C024768 | 3 - Desirable Work | UPPER BUILDING | 3 | C | 4 | Atkins - Fixed Furniture & Fittings - Non Teaching | Renew kitchen base / wall units 1200mm long, including worktop, appliances, ironmongery etc | 1043.75
C025035 | 3 - Desirable Work | (Site) College Town Primary School | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C024696 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 2 | Atkins - Windows & Doors - Frames | Allow to replace vent caps | 60
C024688 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 7 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 1581.6
C025073 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 6850
C025074 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace fluorescent lighting generally on failure with LED luminaires | 6850
C025076 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 5 | Electrical Services - Communications Systems | Consider removal of redundant equipment | 100
C025111 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025113 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 5 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025114 | 3 - Desirable Work | CARETAKER'S BUNGALOW | 3 | B | 10 | Atkins - Mechanical Services - Ventilation | Good Condition | 0
C024807 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 4 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 292.4
C025058 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace any remaining fluorescent lighting generally on failure with LED | 3425
C025061 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025095 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025096 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025099 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 5 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025100 | 3 - Desirable Work | CLASSROOM MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Ventilation | Good Condition | 0
C024832 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 3 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 38
C024836 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 3 | Atkins - Roof - Drainage | Clean out, overhaul and repair existing gutters and downpipes | 4473
C024839 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 4 | Atkins - External Walls - Structure | Repoint joints in brickwork walls | 3159.6
C024843 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 5162.5
C024844 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 3 | Atkins - Redecorations - External | Redecorate external metalwork to rainwater goods - (Gloss) | 1393.5
C024845 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 3 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 964.92
C024846 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Redecorations - External | Redecorate external masonry, cladding & render - (Emulsion) | 2735.2
C024847 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 760
C024867 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 5140.2
C025028 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace any remaining fluorescent lighting generally on failure with LED | 6850
C025032 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Recommend to assess the infrastructure further prior to works being undertaken | 0
C025033 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025034 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025036 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 1000
C025079 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025080 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025083 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 5 | Atkins - Mechanical Services - Heating | Fair Condition - Recommend replacement of Gas Boiler in Year 5 | 0
C025084 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Ventilation | Good Condition | 0
C025086 | 3 - Desirable Work | LOWER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C024799 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 3 | Atkins - Roof - Drainage | Clean out existing guttering | 652.52
C025062 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 5 | Atkins - Electrical Services - Data / Telephone | The installation should be intrusively checked. Where necessary the existing wiring shall be modified with new containment being installed to provide adequate physical separation between LV, ELV and fire alarm systems in accordance with BS EN 50174 and a minimum environmental protection of IP4X. | 3611
C025067 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace any remaining fluorescent lighting generally on failure with LED luminaires | 3425
C025070 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025102 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025103 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025106 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 5 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025107 | 3 - Desirable Work | NURSERY MODULAR | 3 | B | 10 | Atkins - Mechanical Services - Ventilation | Good Condition | 0
C024717 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - External Areas - Hard Surfaced | Renew line markings ( thermoplastic paint) | 895
C025042 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - Lighting | Replace any remaining fluorescent lighting generally on failure with LED | 6850
C025046 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Recommended to assess the infrastructure prior to any works being undertaken. | 500
C025047 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025048 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace TP&N MCB distribution board & associated distribution equipment subject to EICR results | 1500
C025049 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace TP&N MCB distribution board subject to EICR results | 1000
C025050 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace SP&N MCB distribution board subject to EICR results | 500
C025051 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace TP&N MCB distribution board subject to EICR results | 1000
C025052 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Electrical Services - LV Distribution | Replace TP&N MCB distribution board subject to EICR results | 1000
C025087 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025088 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025089 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025091 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Ventilation | Good Condition | 0
C025093 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 10 | Atkins - Mechanical Services - Main Supply - Gas | Good Condition | 0
C025094 | 3 - Desirable Work | UPPER BUILDING | 3 | B | 5 | Atkins - Mechanical Services - Air conditioning | Good Condition | 0
C024698 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 5 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 532
C025071 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Electrical Services - Data / Telephone | Good Condition | 0
C025072 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Electrical Services - Electrical Installation | Rewire installation generally, including allowance for asbestos R&D survey | 10833
C025075 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Electrical Services - Intruder Alarm | Good Condition | 0
C025077 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Electrical Services - LV Distribution | Good Condition | 0
C025112 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025116 | 4 - Long Term Work | CARETAKER'S BUNGALOW | 4 | B | 10 | Atkins - Mechanical Services - Main Supply - Gas | Good Condition | 0
C024808 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | B | 10 | Atkins - Roof - Coverings & Insulation | Good condition | 0
C024810 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | B | 5 | Atkins - Fixed Furniture & Fittings - Non Teaching | Renew kitchen base / wall units 1200mm long, including worktop, appliances, ironmongery etc | 10437.5
C024813 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | B | 10 | Atkins - Sanitary Services - Fittings | Good condition | 0
C025097 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025101 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | B | 10 | Atkins - Mechanical Services - Main Supply - Gas | Good Condition | 0
C024835 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Roof - Coverings & Insulation | NONE but the flat roof should be inspected and cleared of debris annually | 0
C024837 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 5 | Atkins - Redecorations - External | Redecorate external timberwork & cladding - (Gloss) | 3418.5
C024841 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Windows & Doors - Glazing | Good condition | 0
C024848 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 8 | Atkins - Redecorations - External | Redecorate external metalwork to rainwater goods | 1393.5
C024849 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 8 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 964.92
C024850 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Redecorations - External | Redecorate external metalwork to fencing - (Gloss) | 3418.5
C024851 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Redecorations - External | Redecorate external doors & windows generally | 2826.72
C024860 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Sanitary Services - Fittings | Good condition | 0
C024862 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Floors & Stairs - Screed & Finish | Good condition | 0
C024865 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Floors & Stairs - Screed & Finish | Good condition | 0
C024866 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Floors & Stairs - Screed & Finish | Good condition | 0
C024868 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 5 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 3163.2
C024869 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 5 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 1581.6
C024870 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 5 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 8896.5
C024871 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 3163.2
C024872 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 8303.4
C025031 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Electrical Services - Small Power | Good Condition | 0
C025078 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025081 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025085 | 4 - Long Term Work | LOWER BUILDING | 4 | B | 10 | Atkins - Mechanical Services - Main Supply - Gas | Good Condition | 0
C024801 | 4 - Long Term Work | NURSERY MODULAR | 4 | B | 10 | Atkins - Sanitary Services - Fittings | Good condition | 0
C024805 | 4 - Long Term Work | NURSERY MODULAR | 4 | B | 7 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 6128.7
C025104 | 4 - Long Term Work | NURSERY MODULAR | 4 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C025108 | 4 - Long Term Work | NURSERY MODULAR | 4 | B | 10 | Atkins - Mechanical Services - Main Supply - Gas | Good Condition | 0
C025109 | 4 - Long Term Work | NURSERY MODULAR | 4 | B | 10 | Atkins - Mechanical Services - Hot & Cold Water | Good Condition | 0
C024708 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 7 | Atkins - Redecorations - External | Redecorate timber cladding & fencing - (Woodstain) | 152
C024718 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - Windows & Doors - Frames | Good Condition | 0
C024721 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 7 | Atkins - Redecorations - External | Redecorate external metalwork to handrails- (Gloss) | 73.1
C024722 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - Roof - Coverings & Insulation | Good Condition | 0
C024754 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 5 | Atkins - Ceilings - Finish | Renew suspended ceiling | 263.6
C024757 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - External Walls - Linings & Finish | Good condition | 0
C024758 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - Sanitary Services - Fittings | Good condition | 0
C024773 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 5 | Atkins - Redecorations - Internal | Redecorate internally completely, based on Gross Internal Floor Area | 66545.82
C025045 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - Electrical Services - Small Power | Good Condition | 0
C025092 | 4 - Long Term Work | UPPER BUILDING | 4 | B | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025098 | 4 - Long Term Work | CLASSROOM MODULAR | 4 | A | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025082 | 4 - Long Term Work | LOWER BUILDING | 4 | A | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0
C025105 | 4 - Long Term Work | NURSERY MODULAR | 4 | A | 10 | Atkins - Mechanical Services - Heating | Good Condition | 0